## Schedule
Step. | Task | Status | Assignee | Due Date | Priority | Finished at
0 | 準備作業 | Done | ZhangBojiang | 03/02/2026 | Medium | 2026年3月3日 09:46
1 | 新規スタディ作成 | Not started | ZhangBojiang | 03/04/2026 | High
2 | プログラム定数変更 | Not started | ZhangBojiang | 03/04/2026 | Medium
3 | フォルダ名変更 | Not started | ZhangBojiang | 03/04/2026 | Medium
4 | Mapping仕様書の更新（Sitesシート） | Not started | ZhangBojiang | 03/04/2026 | Low
5 | 施設情報をVAPORCONEへアップロード | Not started | ZhangBojiang | 03/04/2026 | High
6 | Mapping仕様書の更新（SuppSettingシート） | Not started | ZhangBojiang | 03/04/2026 | Medium
7 | 移行用EDCの新規作成 | Not started | ZhangBojiang | 03/09/2026 | Low
8 | EDC画面レイアウト変更 | Not started | ZhangBojiang | 03/09/2026 | High
9 | EDCスクリプトファイル変更 | Not started | ZhangBojiang | 03/09/2026 | High
10 | APPファイルのパッケージ化 | Not started | ZhangBojiang | 03/09/2026 | Medium
11 | APPインストール | Not started | ZhangBojiang | 03/09/2026 | Medium
12 | 施設情報をEDCへアップロード | Not started | ZhangBojiang | 03/09/2026 | Medium
13 | スタディデータのパッケージ化 | Not started | ZhangBojiang | 03/06/2026 | Medium
14 | スタディデータをEDCへインポート | Not started | ZhangBojiang | 03/10/2026 | Medium
15 | EDC内でのデータ確認・検証 | Not started | ZhangBojiang | 03/10/2026 | High
16 | データをVAPORCONEへプッシュ | Not started | ZhangBojiang | 03/13/2026 | High
17 | VAPORCONE内でのデータ閲覧範囲設定 | Not started | ZhangBojiang | 03/13/2026 | High
18 | VAPORCONE内でのデータ確認・検証 | Not started | ZhangBojiang | 03/19/2026 | High

## VAPORCONE Info
DEV環境
Code | 工程名 | アクセッション番号 | Study name | スタディ略称 | スタディ正式名 | 研究期間
SDTM202603EN | ENSEMBLE(SDTM) | VCS-0014-001 | ENSEMBLE | ENSEMBLE |  | 2022/10/31-2030/12/31
追加フィルド
スタディ | ドメイン | 変数名 | 表示順 | ラベル（日本語） | LABEL（ENGLISH）
ENSEMBLE | SUPPDS | DSYNFLG | 1 | 再評価実施の有無 | Re-evaluation Performed
ENSEMBLE | SUPPRS | RSCAT1 | 1 | 評価基準の詳細 | Evaluation Criteria Details
ENSEMBLE | SUPPCM | CMTRT1 | 1 | 薬剤名その他詳細 | Drug Name and Other Details
ENSEMBLE | SUPPCM | CMONGO | 2 | 化学療法継続中 | Chemotherapy Ongoing
施設追加
施設 Code | 施設名
DUMMY999 | マッピング用ダミー施設（分析対象外）
サブセット設定
Domain | Field | Description
DM | DOMAIN | Domain
DM | STUDYID | Study ID
DM | USUBJID | Unique Subject ID
DM | RFENDTC | End Date/Time
DM | AGE | Age
DM | SEX | Sex
DM | DTHDTC | Date of Death
DS | DOMAIN | Domain
DS | STUDYID | Study ID
DS | USUBJID | Unique Subject ID
DS | DSTERM | Disposition Event
DS | DSDECOD | Standardized Disposition Term
DS | DSCAT | Category for Disposition
DS | DSSCAT | Subcategory for Disposition
DS | EPOCH | Epoch
DS | DSSTDTC | Start Date of Disposition
MI | DOMAIN | Domain
MI | STUDYID | Study ID
MI | USUBJID | Unique Subject ID
MI | VISIT | Visit
MI | MITESTCD | Pathology Test Short Name
MI | MITEST | Pathology Test Name
MI | MIORRES | Pathology Test Result
MI | MISTRESC | Character Result/Finding in Std Format
PR | DOMAIN | Domain
PR | STUDYID | Study ID
PR | USUBJID | Unique Subject ID
PR | VISIT | Visit
PR | PRCAT | Category
PR | PRTRT | Procedure Name
PR | PRDECOD | Standardized Procedure Name
PR | PRPRESP | Pre-specified
PR | PROCCUR | Occurrence
PR | PRLOC | Procedure Location
PR | PRSTDTC | Start Date of Procedure
PR | PRTPT | Time Point
CM | DOMAIN | Domain
CM | STUDYID | Study ID
CM | USUBJID | Unique Subject ID
CM | EPOCH | Treatment Line
CM | CMSTDTC | Start Date of Medication
CM | CMENDTC | End Date of Medication
CM | CMCAT | Category for Medication
CM | CMSCAT | Subcategory for Medication
CM | CMTRT | Drug/Therapy Name
RS | DOMAIN | Domain
RS | STUDYID | Study ID
RS | USUBJID | Unique Subject ID
RS | VISIT | Visit
RS | EPOCH | Epoch
RS | RSCAT | Category for Assessment
RS | RSSCAT | Subcategory
RS | RSTESTCD | Assessment Short Name
RS | RSTEST | Assessment Name
RS | RSORRES | Assessment Result
RS | RSSTRESC | Std. Format of Assessment Result
RS | RSMETHOD | Method of Assessment
RS | RSDTC | Date/Time of Assessment
SS | DOMAIN | Domain
SS | STUDYID | Study ID
SS | USUBJID | Unique Subject ID
SS | VISIT | Visit
SS | SSTESTCD | Status Short Name
SS | SSTEST | Status Assessment
SS | SSORRES | Survival Result
SS | SSSTRESC | Std Format of Result
SS | SSDTC | Date of Assessment
RF | DOMAIN | Domain
RF | STUDYID | Study ID
RF | USUBJID | Unique Subject ID
RF | RFDESC | File Description
RF | RFCRDTC | Create Date/Time of Collection
RF | RFSIZE | File Size
RF | RFCAT | File Category
RF | RFTYPE | File Type
RF | RFSTYPE | File Subtype
RF | RFVER | File Version
RF | RFXFN | External File Path
RF | RFIFN | Input File Path
RF | RELDOMAIN | Relationship Domain
RF | RELGRPID | Relationship Group ID
RF | RELSEQ | Relationship Sequence Number
RF | RELVAR | Relationship Identifying Variable
RF | VISITNUM | Visit Number
RF | VISIT | Visit
RF | RFGRPID | Group ID
RF | RFSEQ | Sequence Number
RF | RFREFID | Reference ID
GA | DOMAIN | Domain
GA | STUDYID | Study ID
GA | USUBJID | Unique Subject ID
GA | SPDEVID | Method or Assay
GA | GFSEQ | Sequence Number
GA | GFGRPID | Group ID
GA | GFREFID | Specimen ID
GA | GFTESTCD | Genomic Test Short Name
GA | GFTEST | Genomic Test Name
GA | GFTSTDTL | Genomic Test Detail
GA | GFORRES | Genomic Test Result
GA | GFSPEC | Specimen Material Type
GA | VISITNUM | Visit Number
GA | VISIT | Visit
GA | GFDTC | Date of Specimen Collection
GA | ACCESSNUM | Accession Number